## Overall
ITEM | SUB ITEM | ACTION LIST | TIMELINE | OWNER/DEPENDENCY | PROGRESS
1 |  | Green Initiative | 2025
| a | Define vision of the initive by establishing a Green Mission Statement | Q1 25 | FS | Completed. Mission Statement has been created and will be shared with the Staff at the next Staff meeting. 1/30/2025
| b | Create a Green Team to lead the charge internally to engage staff to assist in establishing a green culture | Q1 25 | FS | Team will be a combination of the Sustainability Committe and members of other boards and commissions. Appointments will be made at one of the May BoS meetings.
| c | Assess current environment to understand potential need and impact to create a Sustainability Working Plan | Q2 25 | FS/Consultant
| d | Decide on sustainability initiatives by prioritizing based on impact, effort, cost and feasibility | Q2 25 | BoS
| e | Communicate plans, goals and objectives to stakeholders and define roles and responsibilities of the working plan | Q2 25 | FS
| f | Create time line to begin action steps established by the working plan | Q3 25 | FS
| g | Mange, measure and evaluate the working plan | Ongoing | FS/Consultant
2 |  | Obtain Sustainable CT Bronze Certification | 2025
| a | 1.1.1 -Complete the Sustainable CT Equity Toolkit in its entirety for any Sustainable CT action of your choice. You must have completed the Equity Toolkit process in the last three years to be eligible for points. | Q1 25 | CAO/Sus Comm | Process has begun with initial meeting with Sustainable CT staff and the forming of a Sustainability Committee. Will be working directly with SCT staff to organize next steps and create formal action plan.
| b | 9.1.1 a - Identify the town's staff member(s) responsible for collecting data on municipal solid waste and recycling and reporting that data to the CT DEEP. Ensure that you municipality is up to date with submitting the annual Municipal Recycling Report to DEEP | Q1 25 | CAO/HR | Staff members have been identified (Miller, Gabianelli, Hartshorn, Caruso and Strumello). Main reporting is done by Dee Caruso. Reporting is done on a quarterly basis. Seymour is compliant through the end of 2024. First quarter of 2025 report is in process and will be submitted to the state before the end April.
| c | 12.1.1a - Designate a municipal employee, elected leader, other individual officially designated by the municipality to serve as the liaison for homeless services in your municipality. | Q1 25 | CAO/Sus Comm | CAO Miller will serve in this capacity until it is determined what actual needs are. At that point, the responsibility could be re-assigned to a different person. Appointment will be in May with the establishment of the Green Team. Working with David Morgan at TEAM to determine next steps and possible specific action items.
| d | 6.1.2 - Have at least one municipal elected official and/or staff member and/or members of relevant commissions participate in a Complete Streets training. The training must have taken place in the last three years. | Q1 25 | CAO/Sus Comm | Working with Smart Growth American on setting up the 7 unit web training. Total training is 5.5 hours. Moving timeline completion target to Q2 25.
| e | 10.1.1 - Form an actively engaged local or regional Food Policy Council or Food Alliance, Coalition, or Commission. The committee must be active and meet at least annually. | Q2 25 | CAO/Sus Comm
| f | 2.1.1 - Create a municipal or regional brownfields inventory. For an additional 5 points, create a map of the brownfield sites within your community, either by marking up an existing municipal map manually, or by using an electronic Geographic Information System (GIS) base map. | Q3 25 | CAO/NVCOG
| g | 3.1.1 a - Sponsor or host a program to educate residents and business owners in your community about the value of watersheds and the importance of protecting and restoring them. | Q3 25 | CAO/NVCOG
| h | 5.6.1 b - Create and make available an online checklist detailing the required permit(s), submittals, and steps of your community’s solar permitting process. | Q3 25 | CAO/Land Use
| i | 7.1.1 - Track Energy Use in Municipal and Board of Education Buildings: Maintain current data in ENERGY STAR Portfolio Manager account for all of the municipal and Board of Education buildings listed in the action as defined by ENERGY STAR. You must have at least two full years of benchmarking data within the past three years. | Q3 25 | Operations Department
| j | 11.1.1 - Create a housing committee with diverse membership, ideally reflective of the demographics of your community and regions. The committee must be active and meet at least annually. | Q3 25 | BoS
| k | 4.1.2 - Update and maintain the municipal profile on the CTVisit website. On the CTVIsit Website, link relevant social media platforms for your city or town (like Facebook, Instagram, Twitter, Pinterest, YouTube). Your CTVisit site may not be utilized to satisfy your cultural asset map. Maintain the content, images, and functioning links periodically and provide the date that your CTVisit profile was most recently updated. | Q4 25 | CAO/Sus Comm
| l | 13.1.1 - Implement a sustainability action not listed on the Sustainable CT actions list. You may submit up to two innovation actions per certification cycle. Innovation actions must have been completed or implemented in the last three years. | Q4 25 | CAO/Sus Comm
| m | 8.1 Hold a Sustainability Event | Q4 25 | CAO/Sus Comm
3 |  | Improve Cybersecurity Profile | 2025
| a | Solicit bids for Cybersecurity Audit to improve overall safety of town records | Q1 25 | IT/CAO | Initial conversations have been had about goals and potential scope. Creation of bid specs is currently being worked on.
| b | Utilize cyber insurance provider's email phishing campaigns | Q1 25 | IT/HR | Program implemented and is actively in use. Also doing dark web monitoring for compromised credentials.
| c | Conduct End User Cybersecurity Refresher in conjunction with HR | Q2 25 | IT/HR | Starting process to coordinate between IT and HR
| d | Upgrade Shared Firewall | Q3 25 | IT | Process completed early due to funding availability
| e | Complete MFA for all users | Q4 25 | IT | Currently in process. Town employees expected to be completed by Summer of 2025. BoE employees expected to be completed by Fall of 2025. Was able to start early due to funding availability.
4 |  | Expand Online Access for Town Residents to Services | 2025
| a | Take inventory of what services are currently offered online | Q1 25 | IT/Various Dept. Head | IT has completed list of all current residentail services offered on line
| b | Explore what further services we can offer utilizing existing agreements | Q1 25 | IT/Various Dept. Head | Department heads are speaking with vendors and peers to discuss best practices and to understand available options for review.
| c | Implementation of any expanded online service offerings | Q2 25 | IT/Various Dept. Head | Town Clerk - Phase 1 of the e-recording for all back end operations upgrades have been completed. Phase 2 is underway. It will be completed by May. Will address resident facing functions. Tax Assessor - kiosk installed for resident use to access property cards. Tax Collector - looking at electronic payments for Tax Collector. Targeting summer launch. Building Department - Launch of new online permiting process has been completed. Finance - in final phase of the new online budget software. Transfer station - excepting electronic payments. Misc- completed security camera upgrades. Completed Duo multifactor auth. for logging into domain controlers and servers.
| d | Communication to Community Stakeholders about expanded offerings | Q3 25 | IT/Various Dept. Head
| e | Use of bar code technology to improve resident facing activities for the Town Clerk and Tax Collectors offices | Q3 25 | IT/Various Dept. Head
5 |  | Finance Department | 2025
| a | Update policies and procedures manual. Review and update annually | Q2 25 | Finance
| b | Implement a standardized chart of accounts for all departments | Q2 25 | Finance
| c | Earn GFOA recognition for Distinguished Budget Presentation Award program | Q3 25 | Finance
| d | Expand shared services with the BOE | Q4 25 | Finance/BoE
6 |  | Expansion of Senior Programming - Evening & Weekends | 2025
| a | Begin outreach to working seniors to assess programming needs. | Q2 25 | CS/LC/MA
| b | Promote Programs Via Social Media, Email System and evening open house | Q3 25 | CS/FS
| c | Pilot Additional affordable Evening Programs for Senior Center Members | Q4 25 | Community Services
| d | Expand evening offerings based on feedback | Q4 25 | Community Services
| e | Monitor Attendance Trends and adjust Schedules/programs | Q4 25 | Community Services
7 |  | Afterschool Program Optimization | 2025
| a | Conduct a feasibility study to determine whether maintaining programs at both schools is sustainable. | Q2 25 | Community Services/BoE
| b | Explore the option of transporting students from one school to the other when enrollment is low, using the community center bus | Q2 25 | Community Services/BoE
| c | Implement a trial transportation plan to streamline afterschool programming during periods of low enrollment at one site. | Q3 25 | Community Services/BoE
| d | Monitor program attendance and transportation logistics. Adjust routes, timing, and operations as needed | Q3 25 | Community Services/BoE
| e | Begin promoting the centralized afterschool program to families if the transportation model proves effective. | Q4 25 | Community Services/BoE
8 |  | Community Collaboration - School District | 2025
| a | Meet with school district officials to modify space-sharing agreements | Q3/25 | Community Services/BoE
| b | Identify available space that may be under utilized | Q3/25 | Community Services/BoE
| c | Research joint programs to better serve residents | Q4/25 | Community Services/BoE
| d | Expand Partnerships with schools | Q4/25 | Community Services/BoE
9 |  | Tier 2 Accreditation | 2025
| a | Policy Rewrite | Q4 22 | Chief/Deputy Chief | Completed
| b | Tier 1 Accreditation | Q4 23 | Chief | Completed
| c | On Site | Q4 24 | Chief/Deputy Chief | Postponed until 2025 - Per POSTC Hope is to have on site visit by summer 2025
| d | Tier 2 Accreditation | Q4 25 | Chief/Deputy Chief | Scheduled Site visit by POSTC - Working on new date - possibly sooner
10 |  | Dispatch Transition | 2025
| a. | Selection of Center | Q4 24 | Communications | In progress - meeting to decide
| b. | Funding approval | Q3 25 | Communications | Need to address increase in cost for providing dispatch services
| c. | State Approval | Q1 26 | Communications
| d. | Final Transition | Q2 26 | Chief/DC
11 |  | Automated Speed Enforcement | 2025
| a. | Need Assessment | Q4 24 | Chief | Completed
| b. | Ordinance | Q1 25 | BOS/Chief | Ordinance approved. In mandatory waiting period.
| c. | Site Selection | Q2 25 | Chief/DC/Admin Sgt | Selection of impacted areas for automated enforcement
| d. | Site Preparation | Q3 25 | DPW/ Chief | Implementation of correct signage in compliance with MUTCD
| e. | Vendor Selection | Q3 25 | Chief | Selection of vendor
| f | Implementation | Q4 25 | Chief/DC/Admin Sgt | Implementation of program
12 |  | Prepare for new OSHA rule changes to 1910.156 | 2025
| a | Gather information and hours | Q2 25 | BOC
| b | Create New policies | Q3 25 | BOFC
| c | Propose funding | Q3 25 | BOS,BOF
| d | Ordinance/Charter change if needed | Q3 25 | BOS, Town Council
13 |  | Website Refresh | 2025
| a | Perform a content audit - review all webpages for outdated information, duplicate content, irrelevant keywords, and broken links | Q1 25 | Dept Heads/IT | Ongoing. Working through page by page.
| a.1 | Identify and update outdated content with fresh information | Q1 25 | Dept Heads/IT | Ongoing. Working through page by page.
| a.2 | Consolidate duplicate content pages, redirecting to the most relevant one | Q1 25 | IT/CAO | Ongoing. Working through page by page.
| a.3 | Remove unnecessary or low-value content | Q1 25 | IT/CAO | Ongoing. Working through page by page.
| a.4 | Run site wide broken link checker and fix or remove broken links | Q1 25 | IT/CAO | Ongoing. Working through page by page.
| a.5 | Optimize meta descriptions and page titles for SEO relevance | Q2 25 | IT/CAO
| a.6 | Categorize tasks based on urgency and impact on user experience | Q1 25 | IT/CAO | List being created based on initial findings.
| b | Technical Optimization - analyze website performance and address technical issues impacting loading speed and user experience |  | IT/CAO | IT working with Host provider to make sure load is being balanced.
| b.1 | Use website speed testing tools | Q2 25 | IT/CAO | IT working with Host provider to make sure regular testing is done and website is at optimal speed.
| b.2 | Optimize image sizes and formats for faster loading | Q2 25 | IT/CAO | IT working with Host provide on this.
| b.3 | Enable browser caching | Q2 25 | IT/CAO | No longer needed and has been out moded by current technology.
| b.5 | Review server configuration for optimal performance | Q2 25 | IT/CAO | Service has been virtualized and is running on AWS Cloud
| c | Design and User Experience - evaluate website design consistency, navigation clarity and overall user experience | Q2 25 | IT/CAO
| c.1 | Review site navigation structure for intuitiveness | Q2 25 | IT/CAO
| c..2 | Update outdated design elements | Q2 25 | IT/CAO
| c.3 | Ensure responsive design across devices | Q2 25 | IT/CAO
| c.4 | Conduct user testing to identify usability issues | Q2 25 | IT/CAO
| d | SEO Optimization - analyze website structure and content for SEO best practices | Q2 25 | IT/CAO
| d.1 | Update website sitemap | Q2 25 | IT/CAO
| d.2 | Optimize meta descriptions and title tags for relevant keywords | Q2 25 | IT/CAO
| d.3 | Check for canonicalization issues | Q2 25 | IT/CAO
| d.4 | Review internal linking structure | Q2 25 | IT/CAO
| e | Security Review - assess website security measures and address potential vulnerabilities | Q1 25 | IT/CAO | Assessment done, not vulnerabilites found.
| e.1 | Ensure SSL certificates are up to date | Q1 25 | IT/CAO | Assessement done, all certifcations are up to date.
| e.2 | Regularly scan for malware and security threats | Q1 25 | IT/CAO | Assessment done and all up to date.
| e.3 | Update website software and plugins to latest versions | Q1 25 | IT/CAO | Working with host vendor to stay current with latest version.
| f | Continuously monitor website performance and user feedback to identify areas for further improvement | Ongoing | IT/CAO | Constantly done and will be actively manged going forward.
14 |  | WPCA Future Functional Analysis | 2025
| a | Development and establishment of a Wastewater Facilities Plan | Q3 25 | Town Engineer | Process has begun. Jim Galligan is doing the work.
| b | Review of all overall operations of the WPCA plant, including staffing costs | Q2 25 | Town Engineer/CAO
| c | Review of the existing budget including cash reserves | Q2 25 | Finance/CAO
| d | Review of the existing bill practices and the outstanding receivables | Q2 25 | Finance/CAO
| e | Creation of a next steps plan to establish specific actions to address concerns identified in actions a-d | Q4 25 | Town Engineer/CAO
| f | Review and analyze the potential impact of new development on the existing system capacity | Q4 25 | Town Engineer
| g | Analysis of current rates and creation of future rate model keeping existing management structure vs. establishing new management structure | Q4 25 | Town Engineer/CAO
| h | Review current regulations and keep up to date on upcoming rgulations to ensure the plant can keep up with the needs of clean water regulations. | Q4 25 | Town Engineer/FS
| i | Create and update a Compliance Calendar to ensure permits, reportrs, licenses, and inspections are updated are submitted as required. | Q4 25 | Town Engineer/FS